## Sheet1
| SGQuote | Quote Date | Order Date | WO# | Model No | Sales Person | Price | OLD SN | Available Date | Delivery Date | Requested Delivery Date | Dealer | US Sale | Notes | NEW SN
0 | SG100942 | 2022-12-21 | 2023-02-15 | 10001120 | End Dump 3X | Shelley Holmes | 111886.18 | 4424 | 2023-04-03 | 2023-04-03 |  | Transit Trailer Limited | N | January 02, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 03, 2023 Jan 11, 2023 - SDH - Fixed wording on Calcium Tank, Red paint and spelling error on capacity | 2SVS6D334RM000001
1 | SG101118 | 2023-03-15 |  |  | End Dump 3X | Jason Morgan | 111886.18 | 4494 | 2023-04-03 | 2023-04-03 | 2023-04-03 | Transit Trailer Limited | N | March 15, 2023 - JAAM - As per Change Order, Add Reverse Lights to Rear Middle Plate (Inside Lights), Add 2nd Set of Reverse Lights on Side below Side Rail, between Front & Middle Axle, Add Grain Sock, and Add Compression Locks to Side of Tailgate, Change Box Length to 38 ft. March 16, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 03, 2023 March 24, 2023 - JAAM - As per Change Order, Remove Front D/S Steps. March 24, 2023 - JAAM - As per Change Order, Change Man Door location to Driver's Side. March 24, 2023 - JAAM - As per Change Order, Change Lift Axle from Middle to Front Axle | 2SVS6D336RM000002
2 | SG101102 | 2023-03-10 | 2023-03-14 | 10001166 | End Dump 3X | Shelley Holmes | 111886.18 | 4484 | 2023-04-04 | 2023-04-04 | 2023-04-04 | Transit Trailer Limited | N | March 13, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 04, 2023 | 2SVS6D338RM000003
3 | SG100904 | 2022-12-07 |  |  | End Dump 3X | Jason Morgan | 111886.18 | 9982 | 2023-04-04 | 2023-04-04 | 2023-04-04 | Transit Trailer Limited | N | December 08, 2022 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 04, 2023 March 10, 2023 - JAAM - As per Change Order, Add Compression Locks to Bottom of Tailgate. | 2SVS6D33XRM000004
4 | SG100936 | 2022-12-20 |  |  | Pony Dump 3X17 | Shelley Holmes | 104056.76 | 4446 | 2023-04-04 | 2023-04-04 | 2023-04-04 | Transit Trailer Limited | N | January 02, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 04, 2023 March 13, 2023 - SDH - Updated standard specificaiton form Enginering/production to front fenders to have two brackets | 2SVS6P437RM000005
5 | SG101005 | 2023-01-03 | 2023-02-14 | 10001095 | End Dump 3X | Shelley Holmes | 111886.18 | 4405 | 2023-04-05 | 2023-04-05 | 2023-04-25 | Transit Trailer Limited | N | January 13, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 05, 2023 February 02, 2023 - JAAM - As per Sales Meeting, Updated Steer Axle (Dexter), Added Light Shield Dimension Feb. 22, 2023 – JAAM – As per Signed Change Order, Added Aluminum Round Rod to Tailgate. | 2SVS6D333RM000006
6 | SG101103 | 2023-03-10 | 2023-03-14 | 10001167 | End Dump 3X | Shelley Holmes | 111886.18 | 4485 | 2023-04-05 | 2023-04-05 | 2023-04-05 | Transit Trailer Limited | N | March 13, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 05, 2023 | 2SVS6D335RM000007
7 | SG100905 | 2022-12-07 |  |  | End Dump 3X | Jason Morgan | 111886.18 | 9983 | 2023-04-05 | 2023-04-06 | 2023-04-06 | Transit Trailer Limited | N | December 08, 2022 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 06, 2023 March 10, 2023 - JAAM - As per Change Order, Add Compression Locks to Bottom of Tailgate. | 2SVS6D337RM000008
8 | SG101096 | 2023-03-10 |  |  | Pony Dump 3X17 | Shelley Holmes | 104056.76 | 4496 | 2023-04-07 | 2023-04-07 | 2023-04-07 | Transit Trailer Limited | N | March 13, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 07, 2023 March 13, 2023 - SDH - Updated standard specificaiton form Enginering/production to front fenders to have two brackets March 23, 2023 - JAAM - As per Change Order, Change Board & Tarp Color to Red. Add 6 - 36" Mudflaps in the Rear of the Box (Ship Loose) | 2SVS6P431RM000009
9 | SG101104 | 2023-03-10 | 2023-03-14 | 10001168 | End Dump 3X | Shelley Holmes | 111886.18 | 4486 | 2023-04-10 | 2023-04-10 | 2023-04-10 | Transit Trailer Limited | N | February 03, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to July 03, 2023 Feb. 23, 2023 – JAAM – As per Signed Change Order, Added Aluminum Round Rod to Tailgate. March 13, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 10, 2023 | 2SVS6D335RM000010
10 | SG101088 | 2023-03-07 |  |  | Walking Floor 3X | Jason Morgan | 104044.47 | 8108 | 2023-04-10 | 2023-04-10 | 2023-04-01 | Fleet Maintenance, Inc. | Y | March 09, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 10, 2023 | 2SVS61532RM000011
11 | SG100888 | 2022-12-05 | 2023-01-26 | 10001072 | End Dump 4X | Shelley Holmes | 133490 | 9858 | 2023-04-10 | 2023-04-10 |  | Remorques Lewis Inc. | N | December 05, 2022 - SDH - Changed Est. Delivery Date from May 20, 2021 to March 10, 2023 December 15, 2022 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 11, 2023 January 16, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 13, 2023 March 13, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 10, 2023 | 2SVS6D44XRM000012
12 | SG100922 | 2022-12-14 | 2023-02-15 | 10001136 | Pony Dump 3X17 | Shelley Holmes | 104056.76 | 4422 | 2023-04-11 | 2023-04-11 | 2023-04-11 | Transit Trailer Limited | N | December 15, 2022 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 11, 2023 March 13, 2023 - SDH - Updated standard specificaiton form Enginering/production to front fenders to have two brackets | 2SVS6P435RM000013
13 | SG101028 | 2023-01-03 | 2023-02-14 | 10001113 | End Dump 3X | Shelley Holmes | 111886.18 | 4463 | 2023-04-11 | 2023-04-11 | 2023-04-11 | Transit Trailer Limited | N | January 16, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 11, 2023 Feb. 22, 2023 – JAAM – As per Signed Change Order, Added Aluminum Round Rod to Tailgate. | 2SVS6D332RM000014
14 | SG101105 | 2023-03-10 | 2023-03-14 | 10001169 | End Dump 3X | Shelley Holmes | 111886.18 | 4487 | 2023-04-11 | 2023-04-11 | 2023-04-10 | Transit Trailer Limited | N | March 13, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 11, 2023 | 2SVS6D334RM000015
15 | SG101106 | 2023-03-10 | 2023-03-14 | 10001170 | End Dump 3X | Shelley Holmes | 111886.18 | 4488 | 2023-04-12 | 2023-04-12 | 2023-04-12 | Transit Trailer Limited | N | March 13, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 12, 2023 | 2SVS6D336RM000016
16 | SG101086 | 2023-03-06 | 2023-03-14 | 10001162 | End Dump 3X | Jason Morgan | 111886.18 | 4480 | 2023-04-12 | 2023-04-12 | 2023-04-12 | Transit Trailer Limited | N | March 09, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 12, 2023 | 2SVS6D338RM000017
17 | SG100918 | 2022-12-13 |  |  | End Dump 3X | Shelley Holmes | 111886.18 | 9863 |  | 2023-04-13 |  | Remorques Lewis Inc. | N | January 02, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to May 19, 2023 March 22, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 13, 2023 | 2SVS6D33XRM000018
18 | SG100978 | 2021-12-15 | 2023-01-26 | 10001083 | Walking Floor 3X | Mike Leach | 104044.47 | 8106 |  | 2023-04-14 |  | R.R. Charlesbois Inc | Y | January 02, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to February 14, 2023 January 25, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to March 03, 2023 March 01, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to March 14, 2023 March 20, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 14, 2023 | 2SVS61435RM000019
19 | SG100966 | 2022-10-20 | 2023-01-17 | 10001052 | Live Bottom 4X | Shelley Holmes | 191209.16 | 3217 |  | 2023-04-14 | 2023-03-01 | Remorques Lewis Inc. | N | January 02, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to January 27, 2023 Jan 11, 2023 - SDH - Fixed wording on tailgate operation as spelling error. January 25, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to February 21, 2023 March 01, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to March 31, 2023 March 20, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 14, 2023 | 2SVS6B443RM000020
20 | SG100886 | 2022-12-05 | 2023-01-26 | 10001071 | End Dump 4X | Shelley Holmes | 133490 | 9857 | 2023-04-07 | 2023-04-14 |  | Remorques Lewis Inc. | N | December 05, 2022 - SDH - Changed Est. Delivery Date from May 20, 2021 to March 07, 2023 December 15, 2022 - SDH - Changed Est. Delivery Date from May 20, 2021 to March 10, 2023 December 15, 2022 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 10, 2023 Feb 16, 2023 - SDH - Add 2 way gate, 15 clear lights top and bottom rail, all rear lights to be clear, 6 pairs of ground effect lights March 13, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 07, 2023 March 21, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 14, 2023 | 2SVS6D440RM000021
21 | SG100906 | 2022-12-07 |  |  | End Dump 3X | Jason Morgan | 111886.18 | 9984 | 2023-04-07 | 2023-04-14 | 2023-04-07 | Transit Trailer Limited | N | December 08, 2022 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 07, 2023 March 10, 2023 - JAAM - As per Change Order, Add Compression Locks to Bottom of Tailgate. March 21, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 14, 2023 | 2SVS6D331RM000022
22 | SG101137 | 2023-03-15 |  |  | End Dump 3X | Jason Morgan | 111886.18 | 4503 |  | 2023-04-17 | 2023-04-17 | Transit Trailer Limited | N | March 15, 2023 - JAAM - As per Change Order, Add Reverse Lights to Rear Middle Plate (Inside Lights), Add 2nd Set of Reverse Lights on Side below Side Rail, between Front & Middle Axle, Add Grain Sock, and Add Compression Locks to Side of Tailgate, Change Box Length to 38 ft. March 16, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 03, 2023 March 24, 2023 - JAAM - As per Change Order, Remove Front D/S Steps. March 24, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 17, 2023 March 24, 2023 - JAAM - As per Change Order, Change Man Door location to Driver's Side. March 24, 2023 - JAAM - As per Change Order, Change Lift Axle from Middle to Front Axle to match 4494. | 2SVS6D333RM000023
23 | SG101037 | 2023-01-25 | 2023-02-23 | 10001158 | End Dump 3X | Shelley Holmes | 111886.18 | 4466 | 2023-04-17 | 2023-04-18 | 2023-04-18 | Transit Trailer Limited | N | February 02, 2023 - JAAM - As per Sales Meeting, Fixed Wheels wording, Added Mandoor Location, Fixed Wording for Jug Holder, Removed Hydraulic Hoses February 03, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 18, 2023 | 2SVS6D335RM000024
24 | SG101091 | 2023-03-07 |  |  | Walking Floor 3X | Jason Morgan | 104044.47 | 8109 | 2023-04-17 | 2023-04-18 | 2023-04-01 | Fleet Maintenance, Inc. | Y | March 09, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 18, 2023 | 2SVS61532RM000025
25 | SG100923 | 2022-12-14 | 2023-02-15 | 10001137 | Pony Dump 3X17 | Shelley Holmes | 104056.76 | 4423 | 2023-04-18 | 2023-04-18 | 2023-04-18 | Transit Trailer Limited | N | December 15, 2022 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 18, 2023 March 13, 2023 - SDH - Updated standard specificaiton form Enginering/production to front fenders to have two brackets | 2SVS6P431RM000026
26 | SG101070 | 2023-02-16 |  |  | End Dump 4X | Heather Clark | 133490 | 9333 | 2023-04-18 | 2023-04-19 | 2023-05-08 | Northeast Truck & Trailer Sales | N | March 09, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 19, 2023 | 2SVS6D441RM000027
27 | SG101101 | 2023-03-10 |  |  | End Dump 3X | Shelley Holmes | 111886.18 | 4501 | 2023-04-18 | 2023-04-19 | 2023-04-19 | Transit Trailer Limited | N | March 13, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 19, 2023 | 2SVS6D332RM000028
28 | SG101064 | 2023-02-14 |  |  | End Dump 3X | Jason Morgan | 111886.18 | 4476 |  | 2023-04-20 | 2023-04-20 | Transit Trailer Limited | N | February 23, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 20, 2023 Feb 15, change to all colored lights and rear to be 3 per side in lieu of 13 as per change roder. Feb 28, 2023 - SDH - Add Compression locks on bottom of gate as per Change order | 2SVS6D334RM000029
29 | SG101010 | 2023-01-03 | 2023-02-14 | 10001100 | End Dump 3X | Shelley Holmes | 111886.18 | 4410 | 2023-04-28 | 2023-04-20 | 2023-05-01 | Transit Trailer Limited | N | January 13, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 28, 2023 February 02, 2023 - JAAM - As per Sales Meeting, Updated Steer Axle (Dexter), Added Light Shield Dimension Feb. 23, 2023 – JAAM – As per Signed Change Order, Added Aluminum Round Rod to Tailgate. March 22, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 20, 2023 | 2SVS6D330RM000030
30 | SG101090 | 2023-03-07 | 2023-03-14 | 10001165 | End Dump 3X | Shelley Holmes | 111886.18 | 4483 | 2023-04-21 | 2023-04-21 | 2023-04-21 | Transit Trailer Limited | N | March 09, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 21, 2023 | 2SVS6D332RM000031
31 | SG101078 | 2023-02-16 |  |  | End Dump 4X | Heather Clark | 133490 | 9334 |  | 2023-04-21 | 2023-05-08 | Northeast Truck & Trailer Sales | N | March 09, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to May 05, 2023 March 22, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 21, 2023 | 2SVS6D445RM000032
32 | SG101094 | 2023-03-10 |  |  | Pony Dump 3X17 | Shelley Holmes | 104056.76 | 4500 | 2023-04-21 | 2023-04-21 | 2023-04-21 | Transit Trailer Limited | N | March 13, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 21, 2023 March 13, 2023 - SDH - Updated standard specificatoon from Enginering/production to front fenders to have two brackets March 15, 2023 - added paint code for green | 2SVS6P436RM000033
33 | SG100943 | 2022-12-21 | 2023-02-15 | 10001121 | End Dump 3X | Shelley Holmes | 111886.18 | 4425 | 2023-04-24 | 2023-04-24 |  | Transit Trailer Limited | N | January 02, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 24, 2023 Jan 11, 2023 - SDH - Fixed wording on Calcium Tank, Red paint and spelling error on capacity | 2SVS6D338RM000034
34 | SG100925 | 2022-12-14 | 2023-02-15 | 10001133 | Pony Dump 3X17 | Shelley Holmes | 104056.76 | 9998 | 2023-04-25 | 2023-04-25 | 2023-04-25 | Transit Trailer Limited | N | December 15, 2022 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 25, 2023 March 13, 2023 - SDH - Updated standard specificaiton form Enginering/production to front fenders to have two brackets | 2SVS6P433RM000035
35 | SG101006 | 2023-01-03 | 2023-02-14 | 10001096 | End Dump 3X | Shelley Holmes | 111886.18 | 4406 | 2023-04-25 | 2023-04-25 | 2023-04-26 | Transit Trailer Limited | N | January 13, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 25, 2023 February 02, 2023 - JAAM - As per Sales Meeting, Updated Steer Axle (Dexter), Added Light Shield Dimension Feb. 22, 2023 – JAAM – As per Signed Change Order, Added Aluminum Round Rod to Tailgate. | 2SVS6D331RM000036
36 | SG101007 | 2023-01-03 | 2023-02-14 | 10001097 | End Dump 3X | Shelley Holmes | 111886.18 | 4407 | 2023-04-26 | 2023-04-26 | 2023-04-27 | Transit Trailer Limited | N | January 13, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 26, 2023 February 02, 2023 - JAAM - As per Sales Meeting, Updated Steer Axle (Dexter), Added Light Shield Dimension Feb. 22, 2023 – JAAM – As per Signed Change Order, Added Aluminum Round Rod to Tailgate. | 2SVS6D333RM000037
37 | SG101008 | 2023-01-03 | 2023-02-14 | 10001098 | End Dump 3X | Shelley Holmes | 111886.18 | 4408 | 2023-04-27 | 2023-04-27 | 2023-04-28 | Transit Trailer Limited | N | January 13, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 27, 2023 February 02, 2023 - JAAM - As per Sales Meeting, Updated Steer Axle (Dexter), Feb. 23, 2023 – JAAM – As per Signed Change Order, Added Aluminum Round Rod to Tailgate. | 2SVS6D335RM000038
38 | SG100761 | 2022-09-01 |  |  | 42FHR2X | Shelley Holmes | 62599.5662 | 9506 |  | 2023-04-28 |  | Trans Equipment Co. Inc. | Y | March 03, 2023 - hclark - THIS QUOTE WAS DONE WITH SG101047 THEN CHANGED TO A STARGATE UNIT March 09, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 28, 2023 | 2SVS6D423RM000039
39 | SG101097 | 2023-03-10 |  |  | Pony Dump 3X17 | Shelley Holmes | 104056.76 | 4497 | 2023-04-28 | 2023-04-28 | 2023-04-28 | Transit Trailer Limited | N | March 13, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 28, 2023 March 13, 2023 - SDH - Updated standard specificaiton form Enginering/production to front fenders to have two brackets | 2SVS6P430RM000040
40 | SG101011 | 2023-01-03 | 2023-02-14 | 10001101 | End Dump 3X | Shelley Holmes | 111886.18 | 4411 |  | 2023-05-01 | 2023-05-02 | Transit Trailer Limited | N | January 13, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to May 01, 2023 February 02, 2023 - JAAM - As per Sales Meeting, Updated Steer Axle (Dexter), Added Light Shield Dimension | 2SVS6D335RM000041
41 | SG101013 | 2023-01-13 | 2023-02-14 | 10001103 | End Dump 3X | Shelley Holmes | 111886.18 | 4413 |  | 2023-05-02 | 2023-05-03 | Transit Trailer Limited | N | January 13, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to May 02, 2023 February 02, 2023 - JAAM - As per Sales Meeting, Updated Steer Axle (Dexter), Added Light Shield Dimension Feb. 23, 2023 – JAAM – As per Signed Change Order, Added Aluminum Round Rod to Tailgate. | 2SVS6D337RM000042
42 | SG100937 | 2022-12-20 |  |  | Pony Dump 3X17 | Shelley Holmes | 104056.76 | 4447 |  | 2023-05-02 | 2023-05-02 | Transit Trailer Limited | N | January 02, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to May 02, 2023 March 13, 2023 - SDH - Updated standard specificaiton form Enginering/production to front fenders to have two brackets | 2SVS6P431RM000043
43 | SG101114 | 2023-03-13 |  |  | Frameless End Dump 2X | Jason Morgan | 60836.54 | 4609 |  | 2023-05-02 |  | Wieland Sales Inc. | Y | March 23, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to May 02, 2023 | 2SVS6D128RM000044
44 | SG101014 | 2023-01-03 | 2023-02-14 | 10001104 | End Dump 3X | Shelley Holmes | 111886.18 | 4414 |  | 2023-05-03 | 2023-05-04 | Transit Trailer Limited | N | January 13, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to May 03, 2023 February 02, 2023 - JAAM - As per Sales Meeting, Updated Steer Axle (Dexter), Added Light Shield Dimension Feb. 23, 2023 – JAAM – As per Signed Change Order, Added Aluminum Round Rod to Tailgate. | 2SVS6D332RM000045
45 | SG101016 | 2023-01-03 | 2023-02-14 | 10001106 | End Dump 3X | Shelley Holmes | 111886.18 | 4416 |  | 2023-05-04 | 2023-05-06 | Transit Trailer Limited | N | January 13, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to May 04, 2023 February 02, 2023 - JAAM - As per Sales Meeting, Updated Steer Axle (Dexter), Added Light Shield Dimension Feb. 23, 2023 – JAAM – As per Signed Change Order, Added Aluminum Round Rod to Tailgate. | 2SVS6D334RM000046
46 | SG101012 | 2023-01-03 | 2023-02-14 | 10001102 | End Dump 3X | Shelley Holmes | 111886.18 | 4412 |  | 2023-05-05 | 2023-05-15 | Transit Trailer Limited | N | January 13, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to May 12, 2023 February 02, 2023 - JAAM - As per Sales Meeting, Updated Steer Axle (Dexter), Added Light Shield Dimension Feb. 23, 2023 – JAAM – As per Signed Change Order, Added Aluminum Round Rod to Tailgate. March 22, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to May 05, 2023 | 2SVS6D336RM000047
47 | SG101098 | 2023-03-10 |  |  | Pony Dump 3X17 | Shelley Holmes | 104056.76 | 4498 |  | 2023-05-05 | 2023-05-05 | Transit Trailer Limited | N | March 13, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to May 05, 2023 March 13, 2023 - SDH - Updated standard specificaiton form Enginering/production to front fenders to have two brackets | 2SVS6P43XRM000048
48 | SG101079 | 2023-02-28 |  |  | End Dump 3X | Shelley Holmes | 77361.53 | 4607 |  | 2023-05-08 | 2023-05-02 | Nuss Truck & Equipment | Y | March 09, 2023 - JAAM - As per Sales Meeting, Updated W/O March 09, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to May 08, 2023 | 2SVS6D33XRM000049
49 | SG101075 | 2023-02-21 |  |  | Frameless End Dump 2X | Heather Clark | 60836.54 | 4606 |  | 2023-05-09 |  | Trans Equipment Co. Inc. | Y | February 23, 2023 - hclark - March 13, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to March 23, 2023 March 21, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 13, 2023 March 22, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to May 09, 2023 | 2SVS6D429RM000050
50 | SG101100 | 2023-03-10 |  |  | End Dump 3X | Shelley Holmes | 111886.18 | 4502 |  | 2023-05-09 | 2023-05-09 | Transit Trailer Limited | N | March 13, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to May 09, 2023 | 2SVS6D338RM000051
51 | SG100938 | 2022-12-20 |  |  | Pony Dump 3X17 | Shelley Holmes | 104056.76 | 4448 |  | 2023-05-09 | 2023-05-09 | Transit Trailer Limited | N | January 02, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to May 09, 2023 March 13, 2023 - SDH - Updated standard specificaiton form Enginering/production to front fenders to have two brackets | 2SVS6P433RM000052
52 | SG101080 | 2023-02-28 |  |  | End Dump 3X | Shelley Holmes | 77361.53 | 4608 |  | 2023-05-10 | 2023-05-11 | Nuss Truck & Equipment | Y | March 09, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to May 10, 2023 | 2SVS6D331RM000053
53 | SG101029 | 2023-01-16 |  |  | End Dump 4X | Shelley Holmes | 133490 | 4464 |  | 2023-05-11 | 2023-05-11 | Transit Trailer Limited | N | January 18, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to May 11, 2023 | 2SVS6D444RM000054
54 | SG100917 | 2022-12-05 |  |  | End Dump 4X | Shelley Holmes | 133490 | 9862 |  | 2023-05-12 |  | Remorques Lewis Inc. | N | January 02, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to May 12, 2023 | 2SVS6D446RM000055
55 | SG100880 | 2022-11-24 | 2023-01-26 | 10001076 | End Dump 4X | Jason Morgan | 105392 | 9689 | 2023-04-20 | 2023-05-12 |  | Fleet Maintenance, Inc. | Y | December 06, 2022 - SDH - Changed Est. Delivery Date from May 20, 2021 to February 27, 2023 January 18, 2023 - JAAM - Due to Inventory Shortage, Replace Continental Tires with General RA Tires February 03, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 20, 2023 February 08, 2023 - JAAM - As per Substitution Form, Change Axle/Susp Configuration to Dexter Brand Feb 10, 2023 - SDH - Fixd spread to reflect 49 in. March 22, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to May 12, 2023 | 2SVS6D346RM000056
56 | SG101099 | 2023-03-10 |  |  | Pony Dump 3X17 | Shelley Holmes | 104056.76 | 4499 |  | 2023-05-12 | 2023-05-12 | Transit Trailer Limited | N | March 13, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to May 12, 2023 March 13, 2023 - SDH - Updated standard specificaiton form Enginering/production to front fenders to have two brackets | 2SVS6P431RM000057
57 | SG101015 | 2023-01-03 | 2023-02-14 | 10001105 | End Dump 3X | Shelley Holmes | 111886.18 | 4415 |  | 2023-05-15 | 2023-05-15 | Transit Trailer Limited | N | January 13, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to May 15, 2023 February 02, 2023 - JAAM - As per Sales Meeting, Updated Steer Axle (Dexter), Added Light Shield Dimension Feb. 23, 2023 – JAAM – As per Signed Change Order, Added Aluminum Round Rod to Tailgate. | 2SVS6D330RM000058
58 | SG101017 | 2023-01-03 | 2023-02-14 | 10001107 | End Dump 3X | Shelley Holmes | 111886.18 | 4417 |  | 2023-05-16 | 2023-05-16 | Transit Trailer Limited | N | January 13, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to May 16, 2023 February 02, 2023 - JAAM - As per Sales Meeting, Updated Steer Axle (Dexter), Added Light Shield Dimension Feb. 23, 2023 – JAAM – As per Signed Change Order, Added Aluminum Round Rod to Tailgate. | 2SVS6D332RM000059
59 | SG100963 | 2022-12-05 |  |  | End Dump 4X | Shelley Holmes | 133490 | 9864 |  | 2023-05-16 | 2023-05-02 | Remorques Lewis Inc. | N | January 02, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to May 26, 2023 February 02, 2023 - JAAM - As per Sales Meeting, Updated Qty. of Compression Locks March 22, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to May 16, 2023 | 2SVS6D44XRM000060
60 | SG100939 | 2022-12-20 |  |  | Pony Dump 3X17 | Shelley Holmes | 104056.76 | 4449 |  | 2023-05-16 | 2023-05-16 | Transit Trailer Limited | N | January 02, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to May 16, 2023 March 13, 2023 - SDH - Updated standard specificaiton form Enginering/production to front fenders to have two brackets | 2SVS6P435RM000061
61 | SG100944 | 2022-12-21 | 2023-02-15 | 10001122 | End Dump 3X | Shelley Holmes | 111886.18 | 4426 |  | 2023-05-17 |  | Transit Trailer Limited | N | January 02, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to May 17, 2023 Jan 11, 2023 - SDH - Fixed wording on Calcium Tank, Red paint and spelling error on capacity | 2SVS6D332RM000062
62 | SG100945 | 2022-12-21 | 2023-02-15 | 10001123 | End Dump 3X | Shelley Holmes | 111886.18 | 4427 |  | 2023-05-18 |  | Transit Trailer Limited | N | January 02, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to May 18, 2023 Jan 11, 2023 - SDH - Fixed wording on Calcium Tank, Red paint and spelling error on capacity | 2SVS6D334RM000063
63 | SG100946 | 2022-12-21 | 2023-02-15 | 10001124 | End Dump 3X | Shelley Holmes | 111886.18 | 4428 |  | 2023-05-19 |  | Transit Trailer Limited | N | January 02, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to May 19, 2023 Jan 11, 2023 - SDH - Fixed wording on Calcium Tank, Red paint and spelling error on capacity | 2SVS6D336RM000064
64 | SG100916 | 2022-12-05 |  |  | End Dump 4X | Shelley Holmes | 133490 | 9861 |  | 2023-05-19 |  | Remorques Lewis Inc. | N | January 02, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to May 05, 2023 March 22, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to May 19, 2023 | 2SVS6D449RM000065
65 | SG101095 | 2023-03-10 |  |  | Pony Dump 3X17 | Shelley Holmes | 104056.76 | 4495 |  | 2023-05-19 | 2023-05-19 | Transit Trailer Limited | N | March 13, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to May 19, 2023 March 13, 2023 - SDH - Updated standard specificaiton form Enginering/production to front fenders to have two brackets | 2SVS6P433RM000066
66 | SG101082 | 2023-03-01 |  |  | End Dump 4X | Jason Morgan | 133490 | 9870 |  | 2023-05-19 | 2023-04-01 | Remorques Lewis Inc. | N | March 09, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 07, 2023 March 13, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 20, 2023 March 22, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to May 19, 2023 | 2SVS6D442RM000067
67 | SG101068 | 2023-02-16 |  |  | End Dump 3X | Shelley Holmes | 111886.18 | 9200 |  | 2023-05-23 | 2023-05-23 | Stargate Mgf (2020) Ltd. | N | March 09, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to May 23, 2023 | 2SVS6D333RM000068
68 | SG100947 | 2022-12-21 | 2023-02-15 | 10001125 | End Dump 3X | Shelley Holmes | 111886.18 | 4429 |  | 2023-05-23 |  | Transit Trailer Limited | N | January 02, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to May 23, 2023 Jan 11, 2023 - SDH - Fixed wording on Calcium Tank, Red paint and spelling error on capacity | 2SVS6D335RM000069
69 | SG101022 | 2023-01-16 | 2023-02-15 | 10001138 | Pony Dump 3X17 | Shelley Holmes | 104056.76 | 4458 |  | 2023-05-23 | 2023-05-23 | Transit Trailer Limited | N | January 16, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to May 23, 2023 Feb 10, 2023 - SDH - Add reverse lights and both plugs to be standard plugs, no ISO March 13, 2023 - SDH - Updated standard specificaiton form Enginering/production to front fenders to have two brackets | 2SVS6P437RM000070
70 | SG100976 | 2022-12-22 |  |  | End Dump 2X | Shelley Holmes | 78768 | 9694 | 2023-03-29 | 2023-05-24 |  | R.R. Charlesbois Inc | Y | January 02, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to March 20, 2023 February 14, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to March 24, 2023 February 23, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to March 29, 2023 March 20, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to May 24, 2023 | 2SVS6D029RM000071
71 | SG101083 | 2023-03-02 |  |  | Frameless End Dump 2X | Shelley Holmes | 60836.54 | 9699 |  | 2023-05-25 |  | Trans Equipment Co. Inc. | Y | March 09, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to May 25, 2023 | 2SVS6D428RM000072
72 | SG101084 | 2023-03-06 |  |  | Pony Dump 3X17 | Jason Morgan | 104056.76 | 4479 |  | 2023-05-25 | 2023-05-25 | Transit Trailer Limited | N | March 06, 2023 - JAAM - Pair w/ Truck Box 1331 March 13, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to May 25, 2023 March 13, 2023 - SDH - Updated standard specificaiton form Enginering/production to front fenders to have two brackets | 2SVS6P438RM000073
73 | SG101093 | 2023-03-10 |  |  | End Dump 4X | Shelley Holmes | 133490 | 9871 |  | 2023-05-26 | 2023-05-02 | Remorques Lewis Inc. | N |  | 2SVS6D44XRM000074
74 | SG100979 | 2022-12-22 |  |  | End Dump 3X | Shelley Holmes | 80596 | 9695 | 2023-03-28 | 2023-05-26 |  | R.R. Charlesbois Inc | Y | January 09, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to March 20, 2023 February 23, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to March 28, 2023 March 09, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 21, 2023 March 22, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to May 26, 2023 | 2SVS6D035RM000075
75 | SG100948 | 2022-12-21 | 2023-02-15 | 10001126 | End Dump 3X | Shelley Holmes | 111886.18 | 4430 |  | 2023-05-29 |  | Transit Trailer Limited | N | January 02, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to May 29, 2023 Jan 11, 2023 - SDH - Fixed wording on Calcium Tank, Red paint and spelling error on capacity | 2SVS6D332RM000076
76 | SG100949 | 2022-12-21 | 2023-02-15 | 10001127 | End Dump 3X | Shelley Holmes | 111886.18 | 4431 |  | 2023-05-30 |  | Transit Trailer Limited | N | January 02, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to May 30, 2023 Jan 11, 2023 - SDH - Fixed wording on Calcium Tank, Red paint and spelling error on capacity | 2SVS6D334RM000077
77 | SG101023 | 2023-01-16 | 2023-02-15 | 10001139 | Pony Dump 3X17 | Shelley Holmes | 104056.76 | 4459 |  | 2023-05-30 | 2023-05-30 | Transit Trailer Limited | N | January 16, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to May 30, 2023 Feb 10, 2023 - SDH - Add reverse lights and both plugs to be standard plugs, no ISO March 13, 2023 - SDH - Updated standard specificaiton form Enginering/production to front fenders to have two brackets | 2SVS6P436RM000078
78 | SG100950 | 2022-12-21 | 2023-02-15 | 10001128 | End Dump 3X | Shelley Holmes | 111886.18 | 4432 |  | 2023-05-31 |  | Transit Trailer Limited | N | January 02, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to May 31, 2023 Jan 11, 2023 - SDH - Fixed wording on Calcium Tank, Red paint and spelling error on capacity | 2SVS6D338RM000079
79 | SG101041 | 2023-01-03 | 2023-02-14 | 10001114 | End Dump 3X | Shelley Holmes | 111886.18 | 4470 |  | 2023-06-02 | 2023-06-02 | Transit Trailer Limited | N | February 03, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to June 02, 2023 February 14, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to April 20, 2023 Feb. 22, 2023 – JAAM – As per Signed Change Order, Added Aluminum Round Rod to Tailgate. March 20, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to June 02, 2023 | 2SVS6D334RM000080
80 | SG101107 | 2023-03-10 | 2023-03-14 | 10001171 | End Dump 3X | Shelley Holmes | 111886.18 | 4489 |  | 2023-06-05 | 2023-06-05 | Transit Trailer Limited | N | March 13, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to June 05, 2023 | 2SVS6D336RM000081
81 | SG101108 | 2023-03-10 | 2023-03-14 | 10001172 | End Dump 3X | Shelley Holmes | 111886.18 | 4490 |  | 2023-06-06 | 2023-06-06 | Transit Trailer Limited | N | March 13, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to June 06, 2023 | 2SVS6D338RM000082
82 | SG101040 | 2023-02-02 |  |  | Pony Dump 3X17 | Shelley Holmes | 104056.76 | 4468 |  | 2023-06-06 | 2023-06-06 | Transit Trailer Limited | N | Unit should be identical to 4458 and 4459 February 03, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to June 06, 2023 Feb 10, 2023 - SDH - Add reverse lights and both plugs to be standard plugs, no ISO February 10, 2023 - JAAM - As per SO Meeting, Added New Style Design to the Quote. March 13, 2023 - SDH - Updated standard specificaiton form Enginering/production to front fenders to have two brackets | 2SVS6P433RM000083
83 | SG101061 | 2023-02-14 |  |  | Walking Floor 2X | Jason Morgan | 95388.21 | 8107 |  | 2023-06-06 |  | Butterfield Sales and Equipment | Y | February 14, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to March 21, 2023 March 01, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to June 06, 2023 | 2SVS61426RM000084
84 | SG101042 | 2023-01-03 | 2023-02-14 | 10001115 | End Dump 3X | Shelley Holmes | 111886.18 | 4471 |  | 2023-06-07 | 2023-06-07 | Transit Trailer Limited | N | February 03, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to June 07, 2023 Feb. 23, 2023 – JAAM – As per Signed Change Order, Added Aluminum Round Rod to Tailgate. | 2SVS6D333RM000085
85 | SG101109 | 2023-03-10 | 2023-03-14 | 10001173 | End Dump 3X | Shelley Holmes | 111886.18 | 4491 |  | 2023-06-08 | 2023-06-08 | Transit Trailer Limited | N | March 13, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to June 08, 2023 | 2SVS6D335RM000086
86 | SG100962 | 2022-12-05 |  |  | End Dump 4X | Shelley Holmes | 133490 | 9865 |  | 2023-06-09 | 2023-05-01 | Remorques Lewis Inc. | N | January 02, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to June 09, 2023 | 2SVS6D448RM000087
87 | SG101072 | 2023-02-17 |  |  | Pony Dump 3X17 | Shelley Holmes | 104056.76 | 4477 |  | 2023-06-13 |  | Transit Trailer Limited | N | February 23, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to June 13, 2023 March 13, 2023 - SDH - Updated standard specificaiton form Enginering/production to front fenders to have two brackets | 2SVS6P431RM000088
88 | SG101074 | 2023-02-17 |  |  | Pony Dump 3X17 | Shelley Holmes | 104056.76 | 4478 |  | 2023-06-13 | 2023-06-06 | Transit Trailer Limited | N | February 23, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to June 13, 2023 March 13, 2023 - SDH - Updated standard specificaiton form Enginering/production to front fenders to have two brackets | 2SVS6P435RM000089
89 | SG100940 | 2022-12-21 | 2023-02-15 | 10001129 | End Dump 3X | Shelley Holmes | 111886.18 | 4433 |  | 2023-06-14 |  | Transit Trailer Limited | N | January 02, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to June 14, 2023 Jan 11, 2023 - SDH - Fixed wording on Steer Suspension to reflect IMT (Dexter), added ball valve on Calcium Tank | 2SVS6D337RM000090
90 | SG100941 | 2022-12-21 | 2023-02-15 | 10001130 | End Dump 3X | Shelley Holmes | 111886.18 | 4434 |  | 2023-06-15 |  | Transit Trailer Limited | N | January 02, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to June 15, 2023 Jan 11, 2023 - SDH - Fixed wording on steer axle to say Dexter and Calcium tank to have ball valve | 2SVS6D339RM000091
91 | SG100964 | 2022-12-05 |  |  | End Dump 4X | Shelley Holmes | 133490 | 9866 |  | 2023-06-16 |  | Remorques Lewis Inc. | N | January 02, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to June 16, 2023 February 02, 2023 - JAAM - As per Sales Meeting, Updated Qty. of Compression Locks | 2SVS6D441RM000092
92 | SG100951 | 2022-12-21 | 2023-02-15 | 10001131 | End Dump 3X | Shelley Holmes | 111886.18 | 4435 |  | 2023-06-19 |  | Transit Trailer Limited | N | January 02, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to June 19, 2023 Jan 11, 2023 - SDH - Fixed wording on Calcium Tank, Red paint and spelling error on capacity | 2SVS6D332RM000093
93 | SG100986 | 2023-01-02 |  |  | Pony Dump 3X17 | Shelley Holmes | 104056.76 | 4450 |  | 2023-06-20 | 2023-06-20 | Transit Trailer Limited | N | NEW DESIGN BOX January 02, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to June 20, 2023 March 13, 2023 - SDH - Updated standard specificaiton form Enginering/production to front fenders to have two brackets | 2SVS6P432RM000094
94 | SG100915 | 2022-11-07 |  |  | End Dump 4X | Shelley Holmes | 133490 | 9860 |  | 2023-06-23 | 2023-02-01 | Remorques Lewis Inc. | N | December 15, 2022 - SDH - Changed Est. Delivery Date from May 20, 2021 to March 10, 2023 January 13, 2023 - JAAM - As per Signed Change Order, Added Switch for Lift Axle in Control Box January 13, 2023 - JAAM - As per Signed Change Order, Added Yellow Plug (Added Photo in folder for configuration layout) February 14, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to June 23, 2023 Feb 14, 2023 - SDH - Fixed wording oin tires as should be Continental HDW-2 11R22.5 as per Order. Sales missed adding the wording | 2SVS6D447RM000095
95 | SG101043 | 2023-01-03 | 2023-02-14 | 10001116 | End Dump 3X | Shelley Holmes | 111886.18 | 4472 |  | 2023-06-26 | 2023-06-26 | Transit Trailer Limited | N | February 03, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to June 26, 2023 Feb. 23, 2023 – JAAM – As per Signed Change Order, Added Aluminum Round Rod to Tailgate. | 2SVS6D338RM000096
96 | SG100987 | 2023-01-02 |  |  | Pony Dump 3X17 | Shelley Holmes | 104056.76 | 4451 |  | 2023-06-27 | 2023-06-27 | Transit Trailer Limited | N | NEW DESIGN BOX January 02, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to June 27, 2023 February 02, 2023 - JAAM - As per Sales Meeting, Updated ABS to 4S/3M Added Line for 3/8 Pick Up Plate March 13, 2023 - SDH - Updated standard specificaiton form Enginering/production to front fenders to have two brackets | 2SVS6P433RM000097
97 | SG101052 | 2023-02-08 |  |  | End Dump 4X | Jason Morgan | 105392 | 9698 |  | 2023-06-30 | 2023-05-01 | Fleet Maintenance, Inc. | Y | February 10, 2023 - JAAM - As per S/O Meeting, Change Hoist to 8-5-265. February 14, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to June 30, 2023 February 24, 2023 - JAAM - As per Signed COR, Mount Air Gauge Flush to Front Frame, Change to 39 ft. Frame, 38 ft. Box, 68 in. Wall Height, Drum Brakes instead of Disc Brakes, Remove Vibrator, Tailgate to be hinged on D/S. | 2SVS6D340RM000098
98 | SG101044 | 2023-01-03 | 2023-02-14 | 10001117 | End Dump 3X | Shelley Holmes | 111886.18 | 4473 |  | 2023-07-03 | 2023-07-03 | Transit Trailer Limited | N | February 03, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to July 03, 2023 Feb. 23, 2023 – JAAM – As per Signed Change Order, Added Aluminum Round Rod to Tailgate. | 2SVS6D333RM000099
99 | SG101045 | 2023-01-03 | 2023-02-14 | 10001118 | End Dump 3X | Shelley Holmes | 111886.18 | 4474 |  | 2023-07-04 | 2023-07-04 | Transit Trailer Limited | N | February 03, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to July 04, 2023 Feb. 23, 2023 – JAAM – As per Signed Change Order, Added Aluminum Round Rod to Tailgate. | 2SVS6D336RM000100
100 | SG100988 | 2023-01-02 |  |  | Pony Dump 3X17 | Shelley Holmes | 104056.76 | 4452 |  | 2023-07-04 | 2023-07-04 | Transit Trailer Limited | N | NEW DESIGN BOX January 02, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to July 04, 2023 March 13, 2023 - SDH - Updated standard specificaiton form Enginering/production to front fenders to have two brackets | 2SVS6P43XRM000101
101 | SG101046 | 2023-01-03 | 2023-02-14 | 10001119 | End Dump 3X | Shelley Holmes | 111886.18 | 4475 |  | 2023-07-05 | 2023-07-05 | Transit Trailer Limited | N | Feb. 23, 2023 – JAAM – As per Signed Change Order, Added Aluminum Round Rod to Tailgate. | 2SVS6D33XRM000102
102 | SG101110 | 2023-03-10 | 2023-03-14 | 10001174 | End Dump 3X | Shelley Holmes | 111886.18 | 4492 |  | 2023-07-06 | 2023-07-06 | Transit Trailer Limited | N | March 20, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to July 06, 2023 | 2SVS6D331RM000103
103 | SG101111 | 2023-03-10 | 2023-03-14 | 10001175 | End Dump 3X | Shelley Holmes | 111886.18 | 4493 |  | 2023-07-10 | 2023-07-10 | Transit Trailer Limited | N | March 20, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to July 06, 2023 March 20, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to July 10, 2023 | 2SVS6D333RM000104
104 | SG100989 | 2023-01-02 |  |  | Pony Dump 3X17 | Shelley Holmes | 104056.76 | 4453 |  | 2023-07-11 | 2023-07-11 | Transit Trailer Limited | N | NEW DESIGN BOX January 02, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to July 11, 2023 March 13, 2023 - SDH - Updated standard specificaiton form Enginering/production to front fenders to have two brackets | 2SVS6P434RM000105
105 | SG100990 | 2023-01-02 |  |  | Pony Dump 3X17 | Shelley Holmes | 104056.76 | 4454 |  | 2023-07-18 | 2023-07-18 | Transit Trailer Limited | N | NEW DESIGN BOX January 02, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to July 18, 2023 March 13, 2023 - SDH - Updated standard specificaiton form Enginering/production to front fenders to have two brackets | 2SVS6P438RM000106
106 | SG100991 | 2023-01-02 |  |  | Pony Dump 3X17 | Shelley Holmes | 104056.76 | 4455 |  | 2023-07-25 | 2023-07-25 | Transit Trailer Limited | N | NEW DESIGN BOX January 02, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to July 25, 2023 March 13, 2023 - SDH - Updated standard specificaiton form Enginering/production to front fenders to have two brackets | 2SVS6P431RM000107
107 | SG100952 | 2022-12-21 |  |  | End Dump 3X | Shelley Holmes | 111886.18 | 4436 |  | 2023-08-15 |  | Transit Trailer Limited | N | Jan 11, 2023 - SDH - Fixed wording on Calcium Tank, Red paint and spelling error on capacity March 20, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to August 15, 2023 | 2SVS6D330RM000108
108 | SG100953 | 2022-12-21 |  |  | End Dump 3X | Shelley Holmes | 111886.18 | 4437 |  | 2023-08-15 |  | Transit Trailer Limited | N | Jan 11, 2023 - SDH - Fixed wording on Calcium Tank, Red paint and spelling error on capacity March 20, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to August 15, 2023 | 2SVS6D332RM000109
109 | SG100954 | 2022-12-21 |  |  | End Dump 3X | Shelley Holmes | 111886.18 | 4438 |  | 2023-08-15 |  | Transit Trailer Limited | N | Jan 11, 2023 - SDH - Fixed wording on Calcium Tank, Red paint and spelling error on capacity March 20, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to August 15, 2023 | 2SVS6D339RM000110
110 | SG100955 | 2022-12-21 |  |  | End Dump 3X | Shelley Holmes | 111886.18 | 4439 |  | 2023-08-15 |  | Transit Trailer Limited | N | Jan 11, 2023 - SDH - Fixed wording on Calcium Tank, Red paint and spelling error on capacity March 20, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to August 15, 2023 | 2SVS6D330RM000111
111 | SG100956 | 2022-12-21 |  |  | End Dump 3X | Shelley Holmes | 111886.18 | 4440 |  | 2023-08-15 |  | Transit Trailer Limited | N | Jan 11, 2023 - SDH - Fixed wording on Calcium Tank, Red paint and spelling error on capacity March 20, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to August 15, 2023 | 2SVS6D332RM000112
112 | SG100957 | 2022-12-21 |  |  | End Dump 3X | Shelley Holmes | 111886.18 | 4441 |  | 2023-10-01 |  | Transit Trailer Limited | N | Jan 11, 2023 - SDH - Fixed wording on Calcium Tank, Red paint and spelling error on capacity March 20, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to October 01, 2023 | 2SVS6D334RM000113
113 | SG100958 | 2022-12-21 |  |  | End Dump 3X | Shelley Holmes | 111886.18 | 4442 |  | 2023-10-01 |  | Transit Trailer Limited | N | Jan 11, 2023 - SDH - Fixed wording on Calcium Tank, Red paint and spelling error on capacity March 20, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to October 01, 2023 | 2SVS6D336RM000114
114 | SG100959 | 2022-12-21 |  |  | End Dump 3X | Shelley Holmes | 111886.18 | 4443 |  | 2023-10-01 |  | Transit Trailer Limited | N | Jan 11, 2023 - SDH - Fixed wording on Calcium Tank, Red paint and spelling error on capacity March 20, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to October 01, 2023 | 2SVS6D338RM000115
115 | SG100960 | 2022-12-21 |  |  | End Dump 3X | Shelley Holmes | 111886.18 | 4444 |  | 2023-11-01 |  | Transit Trailer Limited | N | Jan 11, 2023 - SDH - Fixed wording on Calcium Tank, Red paint and spelling error on capacity March 20, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to November 01, 2023 | 2SVS6D33XRM000116
116 | SG100961 | 2022-12-21 |  |  | End Dump 3X | Shelley Holmes | 111886.18 | 4445 |  | 2023-11-01 |  | Transit Trailer Limited | N | Jan 11, 2023 - SDH - Fixed wording on Calcium Tank, Red paint and spelling error on capacity March 20, 2023 - SDH - Changed Est. Delivery Date from May 20, 2021 to November 01, 2023 | 2SVS6D331RM000117